## Overview
| Overview | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Week 1
Week 2 | Hunter works on requirement specifications, other members starts doing research | [6 empty] | Meeting: GUI prototype, Chris and Duc starts working on the GUI
Week 3 | 1/ Problem with deciding GUI prototype. The whole group needs to be more comfortable with HTML/CSS. 2/ Mike works on Use Case. Christ on Risk Management. Duc on Business Model. Hunter continues refining the requirement specs | Class meeting: decide that first delivery date is on the first half of November | [5 empty] | Meeting: developing GUI, problem with connecting Site.Master
Week 4 |  | Class meeting: Chris to continue working on GUI prototype. Hunter to research database connectivity (He has a sample to practice with). Mike to start initial class and ER diagrams. | Duy draftes a more detailed GUI prototype | Duc works on Site.master and default pages. About to work on authentication. Mike: Initial ER and class diagrams completed. Use Cases modified based on Prof Hu's input. | Chris and Duc work on Assets.aspx sidebar and related javascripts | Mike: MVC and database connectivity research. MVC prototype built using Entity Framework connectivity for team to review.
Week 5 | Team reviewed and approved initial ER diagram. Mike to move forward with database and connectivity setup in app. Team discussed MVC design. Mike to test MVC implementation in app with database connection. | Chris completes Sidebar and Search bar/button of Assets.aspx initial GUI prototype. Functionality not added, just visual display. Mike and Duc: Built tables in database based on initial ER diagram. | Mike built tables and entity relations in MSSQL Mike revised ER diagram based on class discussion and notes from Prof Hu. | Mike: Issues with MVC setup in app. Built a prototype with an alternative solution for team to review. Based on feedback Mike to implement alternative solution and abandon MVC, pending further discussion. | Mike: Setup databse connectiviy in app using LinqToSql. Built DataAccess class to provide a layer between views and db connection, only some methods in DA class implemented so far. Built classes to represent some the tables. Built a test page to test db queries and inserts from view through DA class. | Chris: Completed sidebar script for Asset.aspx, added simple example of FIleUpload control to Admin.aspx
Week 6 | Goal: complete upload functionality | Duc modifies upload functionality in Admin.aspx. Having problem with uploaded files shown up only in working copy explorer but not in repository explorer |  | Duc and Chris tried to figure out how to save file into repository instead of working copy, yet unsuccessful! | Mike: Added code to Admin.aspx.cs to populate database with data from file upload. I think basic file upload functionality is now complete. Need to verify with rest of team.
Week 7 |  | Chris: Completed basic search functionality. No results displayed yet. Just able to get the results from the database and store them in a list. Search by tags only, not by file type. Currently just an "Or" search. | Duc: start working on meta tagunctionality. Done with code on webpage. Need modification on DataAccess code. Having problem accessing the SQL database | Chris: Added ability to filter by file types. Researched possible options for displaying thumbnails | Mike worked on SPMP, added methods to the DataAccess class with methods needed for the file tags.
Week 8 |  | Chris: Implemented AJAX image preview functionality | Hunter: Started to look into download capability, able to get save as dialog but cannot get file | Hunter: Began redesign of upload page. | Chris: Fixed search functionality to remove duplicates with implementation of new DataFileComparer class. Modified Admin page. | Mike completed initial SPMP, started researching web security. Need to modify ASP web security to use our database. |  | Documents Updated
Week 9 |  | Chris: Changed Asset page to prevent losing display items on download. Implemented download functionality. (Single File Only) | Chris: Added file name to preview display. | Mike, SPMP version 2 completed, changes made based on Dr. Hu's suggestions.
Week 10 |  | Duc: add download multiple file under a zipfile |  | Hunter: Fixed postback issue with upload | Mike, made changes for web security and user authorization: Built custom AccountMembershipProvider class, built custom AccountRoleProvider class, modified web config to use new custom classes, modified AppUser class to extend MembershipUser, added methods to the DataAccess class with queries needed for user authorization, modified login page to enable user authentication with our database.
Week 11 |  |  |  |  | Mike added methods to the DataAccess class with queries used to log user activity, modified the Master Page to add tabs to link to other pages when logged in as Admin, added blank pages for user maintenance and reports
Week 12 |  |  |  |  | Mike added methods to the DataAccess with queries needed for user maintenance, completed building the user maintenance page
Week 13 |  |  |  | Mike, SPMP version 3 completed. | Mike built the UserReport class, built the FileReport class, added methods to the DataAccess class with queries needed for the reports, completed building the reports page
Week 14 |  |  |  | Mike completed final version of SPMP
Week 15

## Week4
Week 4 (Oct 2 - Oct 9)
Day | Contributor | Description | More details/ Problems?
Monday
Tuesday | Duy | emailed group GUI prototype
Wednesday
Thursday
Friday
Saturday
Sunday